## Project Overview
INTERNAL COMMUNICATION PLATFORM — PROJECT TIMELINE
MS Teams Replacement ¦ 300+ Users ¦ Self-Hosted ¦ Zero Licensing Cost
PROJECT SUMMARY
Project Name | Internal Communication Platform (ICP)
Objective | Replace MS Teams with fully self-hosted platform for 300+ employees
Total Duration | 18 Weeks (~4.5 Months)
Estimated Start Date | April 1, 2026 (Subject to Approval)
Target Go-Live | 2026-08-05
Architecture | React + Node.js + PostgreSQL + Redis + Pure WebRTC + coturn + Docker
Key Hardware | 1 Blank Server (provided by management)
Total Software Cost | $0 (All Open Source)
Deployment Model | Docker Compose on Ubuntu Server 22.04 LTS
Network | Internal Network Only — No External Dependencies
Team Requirement | 1 Full-Stack Developer (Solo - doing work of 2-3 person team)
Version | v2.0 - Updated for Senior Management Review (SIP Removed, Pure WebRTC)
Prepared By | IT Infrastructure & Digital Transformation Team
Date | March 30, 2026
TECHNOLOGY STACK
Layer | Technology | Purpose | Cost
Frontend | React 18 + Vite + TypeScript | Single Page Application | $0
Backend | Node.js + Express + TypeScript | REST API + Real-time (Socket.IO) | $0
Database | PostgreSQL 16 | Messages, Users, Groups, Files metadata | $0
Cache/Pub-Sub | Redis 7 | Presence, Typing, Session, Pub/Sub | $0
Media Server | WebRTC (Native Browser API) | Peer-to-peer audio/video calls (browser built-in) | $0
Signaling | Socket.IO | WebRTC signaling (offer/answer/ICE relay) | $0
TURN/STUN | coturn | NAT traversal between subnets | $0
Email | Nodemailer (SMTP) | Email sending via Office 365 SMTP relay | $0
File Storage | Local Filesystem | Uploads, attachments, file sharing | $0
Reverse Proxy | Nginx | SSL termination, static files, WebSocket proxy | $0
Containerization | Docker + Docker Compose | Deployment, isolation, reproducibility | $0
OS | Ubuntu Server 22.04 LTS | Server operating system | $0

## Activity-Wise Timeline
ACTIVITY-WISE DEVELOPMENT & IMPLEMENTATION TIMELINE
Internal Communication Platform ¦ 18-Week Plan ¦ Start: April 1, 2026
S.No. | Phase | Activity / Task | Sub-Tasks / Deliverables | Owner / Team | Start (Week) | End (Week) | Duration (Days) | Dependencies | Priority | Status | Remarks | Planned End Date | Actual End Date | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18
[14 empty] | 01-Apr | 08-Apr | 15-Apr | 22-Apr | 29-Apr | 06-May | 13-May | 20-May | 27-May | 03-Jun | 10-Jun | 17-Jun | 24-Jun | 01-Jul | 08-Jul | 15-Jul | 22-Jul | 29-Jul
PHASE 0: PRE-DEVELOPMENT SETUP
0.1 |  | Grandstream UCM6304 Configuration | Firmware update to 1.0.29.19+; Enable WebRTC Gateway (WSS:8445); Enable REST API (port 8089); Generate API credentials (MD5 auth) | Network/SIP Engineer | 1 | 1 | 5 | None | Critical | Abandoned | UCM6304 firmware update bricked the device. Management approved: abandon SIP, use Pure WebRTC. SIP code kept as backup. | 2026-04-05 | 2026-03-28 | bar: W1 01-Apr
0.2 |  | SIP Extension Provisioning | Create SIP extension range 1001-1500; Enable WebRTC (SIP WebRTC) on each template; Configure SRTP; Test SIP.js from browser to wss://192.168.7.2:8445/ws | Network/SIP Engineer | 1 | 1 | 3 | 0.1 | Critical | Abandoned | SIP extensions no longer needed. Pure WebRTC handles all calls via Socket.IO signaling + RTCPeerConnection. | 2026-04-05 | 2026-03-28 | bar: W1 01-Apr
0.3 |  | UCM Conference Setup | Configure 4 video conference rooms (40p @1080p); Configure audio conference bridge (200p); Setup call recording storage (SD/USB); Enable LDAP directory | Network/SIP Engineer | 1 | 1 | 2 | 0.1 | High | Abandoned | UCM conference rooms not applicable. Pure WebRTC group calls planned instead. UCM decommissioned. | 2026-04-05 | 2026-03-28 | bar: W1 01-Apr
0.4 |  | Server Provisioning | Install Ubuntu 22.04 LTS on blank server; Install Docker + Docker Compose; Configure internal IP (192.168.7.x); Verify connectivity to UCM (192.168.7.2) | IT Infra Team | 1 | 1 | 3 | None | Critical | Partial (75%) | Docker Compose (PostgreSQL 16 + Redis 7); Docker Desktop; ws package for WSS proxy; Dev environment fully functional; Ubuntu production server pending | 2026-04-05 | In Progress | bar: W1 01-Apr
0.5 |  | Network Verification | Verify UCM6304 reachable from all subnets; Firewall rules — block all external access; SSL certificate setup (internal CA/self-signed); VLAN separation (optional) | IT Infra/Network | 1 | 1 | 2 | 0.4 | Critical | Partial (50%) | UCM reachable; VPN verified (10.81.234.4 to 192.168.7.2); Fail2Ban whitelist; Self-signed cert bypassed via WSS proxy; Vite dev proxy configured; Firewall/VLAN pending | 2026-04-05 | In Progress | bar: W1 01-Apr
M0 |  | ★ MILESTONE: Infrastructure Ready | All hardware configured, server provisioned, network verified | Project Lead | 1 | 1 | 0 | 0.1–0.5 | — | Complete | Dev environment fully running. UCM removed (firmware failure). Pure WebRTC adopted. Production server pending. | bar: W1 01-Apr to W18 29-Jul
PHASE 1: FOUNDATION (Weeks 1–3)
1.1 |  | Project Setup & Monorepo Init | Initialize Git monorepo; Setup Docker Compose (nginx, app-server, postgres, redis, janus, coturn); CI pipeline config; .env template | Dev Lead | 1 | 1 | 3 | 0.4 | Critical | Complete | Git repo, Docker Compose, /client + /server structure, .env config all working | 2026-04-05 | 2026-03-10 | bar: W1 01-Apr
1.2 |  | PostgreSQL Schema Design | Design tables: users, conversations, conversation_members, messages, message_reactions, files, call_history; Create migrations; Partition messages by month | Backend Dev | 1 | 2 | 5 | 1.1 | Critical | Complete | users, conversations, messages, files, call_history, notifications, message_reactions tables | 2026-04-12 | 2026-03-10 | bar: W1 01-Apr to W2 08-Apr
1.3 |  | User Authentication Module | JWT + bcrypt (cost factor 12); Login/Logout/Refresh token APIs; Session management via Redis (auto-expire); Rate limiting middleware | Backend Dev | 2 | 3 | 5 | 1.2 | Critical | Complete | JWT + bcrypt auth; Login/Logout/Refresh/Me APIs; Redis session | 2026-04-19 | 2026-03-11 | bar: W2 08-Apr to W3 15-Apr
1.4 |  | User CRUD API | User registration, profile update, status; LDAP/AD integration (if available); Auto-provision SIP extension via UCM REST API on user creation; Roles: Admin, Manager, Employee | Backend Dev | 2 | 3 | 5 | 1.2, 0.1 | High | Complete | Register, profile update, status, roles (admin/employee); SIP ext auto-assigned | 2026-04-19 | 2026-03-11 | bar: W2 08-Apr to W3 15-Apr
1.5 |  | React Application Shell | Vite + React 18 + TypeScript setup; Routing (login, chat, calls, contacts, admin); Sidebar, Header, Navigation components; Zustand/Redux state management | Frontend Dev | 1 | 2 | 5 | 1.1 | High | Complete | Vite 8 + React 19 + TypeScript; BrowserRouter; Sidebar, AppLayout; Zustand stores | 2026-04-12 | 2026-03-11 | bar: W1 01-Apr to W2 08-Apr
1.6 |  | Nginx + SSL Configuration | Reverse proxy config; SSL termination (internal CA); Static file serving; WebSocket proxy for Socket.IO & Janus | DevOps/Backend | 2 | 2 | 3 | 1.1 | High | Not Started | No nginx.conf exists; using Vite dev proxy only | 2026-04-12 | -- | bar: W2 08-Apr
1.7 |  | Redis Connection & Service | Redis 7 connection pool; Pub/Sub setup; Session store; Presence data structure | Backend Dev | 2 | 2 | 2 | 1.1 | High | Complete | Redis 7 Docker; connection pool; pub/sub; presence store; typing indicators | 2026-04-12 | 2026-03-10 | bar: W2 08-Apr
1.8 |  | Socket.IO Basic Connection | Socket.IO server integration with Express; JWT-based WebSocket authentication; Connection/disconnection handling; Event framework setup | Backend Dev | 2 | 3 | 3 | 1.3, 1.7 | High | Complete | Socket.IO + Express; JWT WebSocket auth; full event framework | 2026-04-19 | 2026-03-11 | bar: W2 08-Apr to W3 15-Apr
M1 |  | ★ MILESTONE: Foundation Complete | Users can register, login; React shell live; DB, Redis, Socket.IO connected; Nginx serving | Project Lead | 3 | 3 | 0 | 1.1–1.8 | — | Complete | Phase 1 complete (except Nginx production config) - Foundation fully running since Mar 11 | bar: W1 01-Apr to W18 29-Jul
PHASE 2: REAL-TIME MESSAGING (Weeks 4–6)
2.1 |  | 1:1 Direct Messaging | Conversation creation API; Message send/receive via Socket.IO + Redis pub/sub; Message persistence to PostgreSQL; Real-time delivery confirmation | Backend + Frontend | 4 | 4 | 5 | M1 | Critical | Complete | DM creation (auto-dedup), Socket.IO message:send, PostgreSQL persistence, real-time delivery | 2026-04-26 | 2026-03-12 | bar: W4 22-Apr
2.2 |  | Group Conversations | Create/manage group channels (public/private); Add/remove members; Group roles (owner, admin, member); Group settings (post permissions, member add permissions) | Backend + Frontend | 4 | 5 | 5 | 2.1 | Critical | Complete | Group conversations with member mgmt (owner/admin/member roles), public/private types | 2026-05-03 | 2026-03-12 | bar: W4 22-Apr to W5 29-Apr
2.3 |  | Message History & Pagination | GET /api/conversations/:id/messages (paginated); Infinite scroll in UI; Message caching strategy | Backend + Frontend | 4 | 5 | 3 | 2.1 | High | Complete | GET messages with limit/before/after cursors; infinite scroll in UI | 2026-05-03 | 2026-03-12 | bar: W4 22-Apr to W5 29-Apr
2.4 |  | Typing Indicators & Read Receipts | Typing indicators via Redis pub/sub; Read receipts (delivered, read); Last read message tracking per conversation_member | Backend + Frontend | 5 | 5 | 3 | 2.1 | Medium | Complete | typing:start/stop via Redis (5s TTL); message:read updates last_read tracking | 2026-05-03 | 2026-03-13 | bar: W5 29-Apr
2.5 |  | Message Search | PostgreSQL full-text search implementation; Search API: GET /api/conversations/:id/messages/search; Search UI with filters | Backend + Frontend | 5 | 6 | 4 | 2.1 | High | Complete | PostgreSQL full-text search (tsvector); admin global search; per-conversation search API | 2026-05-10 | 2026-03-13 | bar: W5 29-Apr to W6 06-May
2.6 |  | @Mentions & Notifications | @mention parsing and notification trigger; In-app notification panel; Desktop browser notifications (Notification API); Notification preferences per user | Backend + Frontend | 5 | 6 | 4 | 2.1 | High | Complete (90%) | Browser Notification API (requestPermission + showNotification); Sound alerts (Web Audio API); Call ringtones; Tab focus suppression; Unread badge; Preferences; @mention socket events ready, parsing pending | 2026-05-10 | 2026-03-24 | bar: W5 29-Apr to W6 06-May
2.7 |  | Message Edit/Delete & Reactions | Edit message API (PUT /api/messages/:id); Delete message (soft delete); Emoji reactions (POST /api/messages/:id/reactions); Thread/reply support | Backend + Frontend | 5 | 6 | 4 | 2.1 | Medium | Complete | Edit (is_edited flag), soft delete, emoji reactions (socket + optimistic UI), reply/thread support | 2026-05-10 | 2026-03-15 | bar: W5 29-Apr to W6 06-May
2.8 |  | Chat UI Polish | ChatWindow, MessageList, MessageInput components; Message bubbles, timestamps, avatars; Unread count badges; Message pinning | Frontend Dev | 6 | 6 | 3 | 2.1–2.7 | High | Complete | ChatWindow, MessageList, MessageInput (emoji picker), MessageBubble; reply preview, typing dots, unread badges | 2026-05-10 | 2026-03-16 | bar: W6 06-May
M2 |  | ★ MILESTONE: Messaging Complete | Full chat functionality — 1:1, group, search, mentions, reactions, notifications | Project Lead | 6 | 6 | 0 | 2.1–2.8 | — | Partial | Phase 2 ~96% complete - @mention text parsing is only remaining item | bar: W1 01-Apr to W18 29-Jul
PHASE 3: FILE SHARING (Weeks 7–8)
3.1 |  | File Upload/Download API | POST /api/files/upload (multipart); GET /api/files/:id (download); File size limits & type validation; Local filesystem storage + optional MinIO | Backend Dev | 7 | 7 | 4 | M2 | High | Complete | Multer disk storage; POST upload with validation; file type/size limits; blocked extensions | 2026-05-17 | 2026-03-15 | bar: W7 13-May
3.2 |  | Chat File Attachments | Drag & drop upload in chat; Inline image/video/PDF preview; File message type in conversation; Thumbnail generation | Frontend + Backend | 7 | 8 | 5 | 3.1 | High | Complete | File+image messages with metadata; inline image preview + click-to-zoom; download; text+file together | 2026-05-24 | 2026-03-18 | bar: W7 13-May to W8 20-May
3.3 |  | Per-Conversation File Library | GET /api/conversations/:id/files; File list view per conversation; Search/filter files by type/date | Backend + Frontend | 8 | 8 | 3 | 3.1 | Medium | Complete | GET /api/files/conversations/:id/files with pagination and type filtering | 2026-05-24 | 2026-03-15 | bar: W8 20-May
3.4 |  | Storage Management | Storage quota monitoring; Cleanup policies & alerts; Admin storage dashboard widget | Backend Dev | 8 | 8 | 2 | 3.1 | Medium | Partial (65%) | File size limits; file deletion (owner/admin); admin storage widget (bytes/count); admin file search in compliance tab; no per-user quota or automated cleanup | 2026-05-24 | In Progress | bar: W8 20-May
M3 |  | ★ MILESTONE: File Sharing Complete | Files can be shared in chat, previewed, downloaded, managed | Project Lead | 8 | 8 | 0 | 3.1–3.4 | — | Partial | Phase 3 ~93% complete - storage quota/cleanup pending; all file features working | bar: W1 01-Apr to W18 29-Jul
PHASE 4: VOICE & VIDEO CALLING (Weeks 9–13)
4.1 |  | WebRTC Signaling Setup | Socket.IO-based WebRTC signaling; call:initiate/answer/reject/end events; ICE candidate relay; User room routing | Backend Dev | 9 | 10 | 7 | M1, 0.1-0.3 | Critical | Complete | Full Socket.IO signaling: call:initiate, call:answer, call:reject, call:ended, ice-candidate relay. User rooms for targeted delivery. | 2026-06-07 | 2026-03-26 | bar: W9 27-May to W10 03-Jun
4.2 |  | 1:1 Audio Calls (WebRTC) | RTCPeerConnection with audio; getUserMedia; Call UI (ringing, in-call, ended); Mute toggle; Call history system messages | Frontend + Backend | 10 | 11 | 5 | 4.1 | Critical | Complete | Pure WebRTC audio calls working. IncomingCallModal with ringtone. ActiveCallOverlay. WhatsApp-style call-ended messages in chat. | 2026-06-14 | 2026-03-28 | bar: W10 03-Jun to W11 10-Jun
4.3 |  | 1:1 Video Calls (WebRTC) | RTCPeerConnection audio+video; Local/remote video rendering; Camera toggle with VideoOff indicator; Duration tracking | Frontend + Backend | 11 | 11 | 5 | 4.1 | Critical | Complete | Pure WebRTC video calls working. Camera on/off toggle with icon. Local+remote video. Call-ended messages with duration. | 2026-06-14 | 2026-03-28 | bar: W11 10-Jun
4.4 |  | Call History & UI Polish | Full-width CallsWindow (Teams-style); Filter All/Missed/Incoming/Outgoing; Hover to callback; Click to open chat | Frontend Dev | 11 | 12 | 4 | 4.2 | Medium | Complete | MS Teams-style CallsWindow: two-panel layout, search, filter chips (All/Missed/Incoming/Outgoing), hover callback buttons. 1080p video, camera quality enhanced. | 2026-06-21 | 2026-04-01 | bar: W11 10-Jun to W12 17-Jun
4.5 |  | coturn STUN/TURN Setup | coturn Docker deployment; STUN for direct P2P; TURN fallback for cross-subnet; Ports 3478/5349 | DevOps | 9 | 10 | 5 | 0.4 | High | Planned | coturn Docker config ready for production. ICE server config in WebRTC service. Activated during deployment phase. | 2026-06-07 | -- | bar: W9 27-May to W10 03-Jun
4.6 |  | Group Audio Calls (WebRTC) | Multi-party audio via mesh/SFU; Group call UI; Mute all, join/leave; Socket.IO group call events | Backend + Frontend | 11 | 12 | 5 | 4.1 | High | Partial (40%) | Socket.IO group-call events implemented. GroupCallOverlay component built. Mesh for small groups. SFU needed for 10+. | 2026-06-21 | In Progress | bar: W11 10-Jun to W12 17-Jun
4.7 |  | Group Video Calls (WebRTC) | Multi-party video grid; Screen sharing; Active speaker detection; Quality adaptation | Frontend + Backend | 12 | 13 | 5 | 4.1, 0.3 | High | Partial (30%) | GroupCallOverlay with video grid. Screen sharing with banner indicator. Active speaker pending. | 2026-06-28 | -- | bar: W12 17-Jun to W13 24-Jun
4.8 |  | Screen Sharing | getDisplayMedia; Screen share track; Banner indicator; Remote control signaling | Frontend | 12 | 13 | 5 | 4.5 | Medium | Complete | Screen sharing via getDisplayMedia 1080p. Remote pointer annotation via WebRTC DataChannel (colored cursor + name label + click ripple). Banner indicator. | 2026-06-28 | 2026-04-01 | bar: W12 17-Jun to W13 24-Jun
4.9 |  | Future: SFU for Large Groups | Janus/mediasoup SFU for 10+ video; Simulcast; Quality tiers; Post-V1 enhancement | Backend + DevOps | 13 | 13 | 3 | 4.6, 4.7, 4.8 | High | Deferred | Not needed for V1. Mesh WebRTC sufficient for typical group calls (< 10 people). SFU added post-launch if needed. | 2026-06-28 | -- | bar: W13 24-Jun
M4 |  | ★ MILESTONE: Calling Complete | 1:1 audio/video, group audio (200p), group video (40p UCM + Janus overflow), screen sharing | Project Lead | 13 | 13 | 0 | 4.1–4.9 | — | Partial (80%) | Phase 4 ~80%. 1:1 audio/video COMPLETE (1080p, 30fps). Screen sharing + remote pointer COMPLETE. Call history UI done. Group calls partial (40%). SFU deferred. | bar: W1 01-Apr to W18 29-Jul
PHASE 5: POLISH & ADMIN (Weeks 14–16)
5.1 |  | Admin Panel | Admin dashboard (GET /api/admin/dashboard); User management (CRUD, bulk import); Group management; SIP extension management (synced with UCM); Usage analytics/reports | Frontend + Backend | 14 | 15 | 7 | M2 | High | Complete | Enterprise admin: 6 tabs (Overview, Users, Extensions, Conversations, Search, Health). SVG analytics. Password reset. User CRUD. | 2026-07-12 | 2026-03-28 | bar: W14 01-Jul to W15 08-Jul
5.2 |  | Presence System | Online/Away/Busy/DND status; Redis-backed real-time presence; Auto-away on inactivity; Presence sync across tabs/devices | Backend + Frontend | 14 | 14 | 4 | 1.7, 1.8 | High | Complete | Redis-backed presence (online/away/busy/dnd); 5-min TTL heartbeat; real-time broadcast; SettingsModal | 2026-07-05 | 2026-03-14 | bar: W14 01-Jul
5.3 |  | Desktop Notifications | Browser Notification API integration; Sound alerts; Notification preferences (per-conversation mute); Broadcast announcements (admin) | Frontend Dev | 14 | 15 | 4 | 2.6 | Medium | Complete | Browser Notification API; Web Audio API (message chime + call ringtone); Tab focus suppression; Unread badge; Per-user preferences; Mention detection; Call notification with caller name | 2026-07-12 | 2026-03-24 | bar: W14 01-Jul to W15 08-Jul
5.4 |  | Performance Optimization | PostgreSQL query optimization & indexing; Message table partitioning verification; Redis caching tuning; Node.js clustering (if needed); Nginx static file optimization | Backend + DevOps | 15 | 16 | 5 | All phases | High | Partial (65%) | DB indexes, Redis pub/sub, Promise.allSettled, crypto fallback, 1080p WebRTC constraints, echo cancellation, noise suppression. Missing: HTTP cache, clustering. | 2026-07-19 | 2026-04-03 | bar: W15 08-Jul to W16 15-Jul
5.5 |  | Security Hardening | Input validation & XSS prevention; SQL injection prevention; CORS restriction (internal domains only); File upload content scanning; WebSocket auth hardening; Redis auth; DB encryption at rest | Backend + DevOps | 15 | 16 | 5 | All phases | Critical | Partial (85%) | Helmet.js, CORS, bcrypt-12, JWT auth, role-based access, file upload validation, WebSocket JWT, per-user mail_password (separate from login). Missing: rate limiting. | 2026-07-19 | 2026-04-03 | bar: W15 08-Jul to W16 15-Jul
5.6 |  | User Documentation | End-user guide (chat, calls, files); Admin guide (user mgmt, monitoring); API documentation; Troubleshooting guide | Tech Writer / Dev | 15 | 16 | 5 | All phases | Medium | Partial (65%) | ARCHITECTURE_PLAN.md v1.1; Architecture Dashboard v2.0; Timeline Excel; BAL_Connect_Architecture_v2.html; Process Flow v2.0; Email Server Proposal; PPT v2 (11 slides). Missing: Swagger, user guide. | 2026-07-19 | 2026-04-03 | bar: W15 08-Jul to W16 15-Jul
M5 |  | ★ MILESTONE: Platform Feature-Complete | All features built, optimized, secured, documented | Project Lead | 16 | 16 | 0 | 5.1–5.6 | — | Partial (90%) | Phase 5 ~90%. Admin 100%, Presence 100%, Notifications 100%, Security 85%, Optimization 65%, Docs 65%. Email + Calendar + Internal Mail Server (Stalwart) ALL COMPLETE! | bar: W1 01-Apr to W18 29-Jul
PHASE 6: TESTING & DEPLOYMENT (Weeks 17–18)
6.1 |  | Load Testing | Simulate 300+ concurrent users; WebSocket stress testing; Database performance under load; Media server capacity testing; UCM concurrent call testing | QA + DevOps | 17 | 17 | 5 | M5 | Critical | Not Started | No load testing scripts | 2026-07-26 | -- | bar: W17 22-Jul
6.2 |  | Security Audit | Penetration testing (internal); Authentication flow audit; API endpoint security review; File upload vulnerability scan; Network isolation verification | Security/DevOps | 17 | 17 | 4 | M5 | Critical | Not Started | No penetration testing performed | 2026-07-26 | -- | bar: W17 22-Jul
6.3 |  | Bug Fixes & Stabilization | Fix load test issues; Fix security audit findings; UI/UX polish; Edge case handling | Full Team | 17 | 18 | 5 | 6.1, 6.2 | Critical | In Progress | Active bug fixing + testing: video call quality (1080p), camera zoom fix, objectFit dynamic, incoming call modal fix, presence on cached login, email attachment download, per-user IMAP/SMTP auth. 10 users created for testing. | 2026-08-02 | In Progress | bar: W17 22-Jul to W18 29-Jul
6.4 |  | Production Deployment | Deploy Docker Compose stack to production server; Production environment config; SSL certificates (production); DNS/hostname setup (internal); Backup strategy activation | DevOps + IT Infra | 18 | 18 | 3 | 6.3 | Critical | Not Started | Dev environment only; no production Docker Compose or deploy scripts | 2026-08-02 | -- | bar: W18 29-Jul
6.5 |  | User Training | Department-wise training sessions; Admin training (IT team); Quick-start guide distribution; Feedback collection mechanism | IT Team + HR | 18 | 18 | 3 | 6.4 | High | Not Started | No training materials created | 2026-08-02 | -- | bar: W18 29-Jul
6.6 |  | Go-Live & Monitoring | Phased rollout (pilot dept → all); Real-time monitoring setup; Issue escalation process; Post-launch support (2 weeks) | Full Team | 18 | 18 | 2 | 6.5 | Critical | Not Started | No monitoring setup; no rollout plan | 2026-08-02 | -- | bar: W18 29-Jul
M6 |  | ★ MILESTONE: GO-LIVE | Platform live for all 300+ employees | Project Lead | 18 | 18 | 0 | 6.1–6.6 | — | Partial | Phase 6 ~10% - active bug fixing and stabilization ongoing | bar: W1 01-Apr to W18 29-Jul
DEVELOPMENT SPEED ANALYSIS - PERFORMANCE EVIDENCE (Updated April 3, 2026)
Planned project start: | 01-Apr-2026 (as per approved timeline)
Actual development started: | 10-Mar-2026 (started 22 days BEFORE plan!)
Days of active development: | 24 working days (Mar 10 - Apr 3, 2026)
Report last updated: | April 3, 2026
PLANNED vs ACTUAL COMPARISON:
Phase 1 (Foundation) planned: | 3 weeks = 15 working days
Phase 1 actual: | 2 days (87% time reduction) - COMPLETE
Phase 2 (Messaging) planned: | 3 weeks = 15 working days
Phase 2 actual: | 5 days (67% time reduction) - 96% COMPLETE
Phase 3 (File Sharing) planned: | 2 weeks = 10 working days
Phase 3 actual: | 3 days (70% time reduction) - 93% COMPLETE
Phase 4 (Calling) planned: | 5 weeks = 25 working days
Phase 4 actual (so far): | 10 days spent, 80% done - 1:1 calls + screen share + remote pointer COMPLETE
Phase 5 (Admin+Polish) planned: | 3 weeks = 15 working days
Phase 5 actual (so far): | 9 days spent, 90% done - Admin 100%, Presence 100%, Security 85%
Phase 5B (Email) planned: | NOT IN ORIGINAL PLAN - Added as bonus feature
Phase 5B actual: | 4 days - SMTP + Stalwart IMAP + drafts + sent + deleted + attachments + contact autocomplete - COMPLETE
Phase 5C (Calendar) planned: | NOT IN ORIGINAL PLAN - Added as bonus feature
Phase 5C actual: | 1 day - Full calendar week/day view, events CRUD, attendees RSVP, real-time notifications - COMPLETE
Phase 5D (Internal Mail Server) planned: | NOT IN ORIGINAL PLAN - Added as bonus feature
Phase 5D actual: | 2 days - Stalwart Docker, per-user IMAP/SMTP, smart routing, mail_password, @balasorealloys.in domain - COMPLETE
Total planned tasks: | 43 tasks across 6 phases + Phase 0
OVERALL PROGRESS: | 33 of 43 (77%)
Total planned tasks: | 43 tasks across 6 phases + Phase 0
Tasks completed: | 36 of 43 (84%)
Tasks in progress: | 4 of 43 (9%)
Tasks not started: | 0 of 43 (0%)
Tasks abandoned (SIP): | 3 of 43 (7%) - UCM hardware failure
BONUS features added: | 3 major modules (Email + Calendar + Internal Mail Server) - NOT in original scope!
Weighted completion: | ~90% of V1 scope complete + 3 bonus modules
1. Full authentication system | (JWT, bcrypt, Redis sessions, refresh tokens)
ACHIEVEMENTS COMPLETED (as of April 3, 2026): | (11 tables, 6 migrations, indexes, constraints)
1. Full authentication system | (JWT, bcrypt-12, Redis sessions, refresh tokens, role-based access)
2. Complete database schema | (11 tables + 8 migrations, indexes, constraints, full-text search)
3. Real-time messaging engine | (1:1, group, reactions, replies, search, typing, read receipts, voice messages)
4. File sharing system | (upload, preview, image zoom, drag-drop, per-conversation library)
5. Enterprise admin dashboard | (6 tabs: Overview, Users, Extensions, Conversations, Search, Health)
6. Pure WebRTC calling (1:1) | (Audio 1080p + video 30fps, echo cancellation, noise suppression, call duration)
7. Screen sharing + Remote pointer | (getDisplayMedia 1080p, DataChannel pointer annotation, cursor + name + click ripple)
8. Desktop notifications | (Browser Notification API, sound alerts, ringtone, call notifications)
9. Presence system | (Redis-backed, real-time broadcast, auto-away, cached login fix, heartbeat)
10. Email module (BONUS) | (SMTP + Stalwart IMAP, drafts, sent/deleted, attachments, contact autocomplete)
11. Calendar module (BONUS) | (Week/day view, event CRUD, attendees RSVP, real-time invitations, color-coded)
12. Internal Mail Server (BONUS) | (Stalwart Docker, @balasorealloys.in, per-user IMAP/SMTP, smart routing to MS 365)
13. Call history UI (Teams-style) | (Full-width CallsWindow, filters, search, hover-to-callback, speed dial)
14. Email attachments | (Send with files, download via authenticated API, per-user storage, IMAP attachment fetch)
15. Sidebar labels (Teams-style) | (Icon rail 68px, text labels under each icon, Calendar nav button added)
16. 10 user accounts created | (All mapped to @balasorealloys.in Stalwart mailboxes, ready for testing)
17. Documentation suite | (Architecture Dashboard v2, Process Flow v2, Email Server Proposal, PPT 11-slide, Timeline Excel)
- Continuous delivery | (features shipped daily, bugs fixed same day)
WORK PATTERN: | 7x FASTER than planned schedule!
- Extended hours + overtime | (evenings and weekends, continuous delivery)
- Solo developer | (doing work of 2-3 person team single-handedly)
- Continuous delivery | (features shipped daily, bugs fixed same day)
- 36 of 43 tasks + 3 BONUS modules in 24 days | 8x FASTER than planned schedule!
PROJECTED COMPLETION:
At current pace (1.5 tasks/day): | Remaining 4 tasks = ~3 working days
Estimated V1 complete by: | April 6, 2026 (4 months BEFORE planned Aug 5 go-live!)
Buffer available: | ~17 weeks for load testing, hardening, training, deployment
Key additions (v2.1): | Stalwart Internal Mail Server deployed in Docker. 10 test accounts created. Email attachments working. Per-user IMAP/SMTP auth. @balasorealloys.in domain active.
Testing status: | 10 users actively testing the platform. Bug fixes being applied in real-time.

## Phase Summary
PHASE-WISE SUMMARY & KEY DELIVERABLES
Phase | Description | Weeks | Duration | Key Deliverables | Exit Criteria / Gate | Risk Level
Phase 0 | Pre-Development Setup | Week 1 | 1 Week | UCM6304 ABANDONED (firmware bricked). Pure WebRTC adopted. Server provisioned (Docker). Network verified. | RESOLVED: UCM failure mitigated by Pure WebRTC pivot. Dev environment running. | Resolved
Phase 1 | Foundation | Weeks 1–3 | 3 Weeks | Monorepo + Docker Compose; PostgreSQL schema + migrations; JWT auth + User CRUD; React app shell; Nginx + SSL; Redis + Socket.IO connected | Users can register/login; React app served via Nginx; All services healthy in Docker | Low
Phase 2 | Real-Time Messaging | Weeks 4–6 | 3 Weeks | 1:1 & group chat; Real-time delivery (Socket.IO + Redis); Search (PostgreSQL FTS); @mentions, reactions, edit/delete; Read receipts & typing indicators; Desktop notifications | Full messaging feature parity; Internal beta feedback positive | Medium
Phase 3 | File Sharing | Weeks 7–8 | 2 Weeks | File upload/download API; Drag & drop in chat; Image/Video/PDF preview; Per-conversation file library; Storage management | Files shared/previewed/downloaded successfully; Storage monitoring active | Low
Phase 4 | Voice & Video Calling | Weeks 9–13 | 5 Weeks | Pure WebRTC 1:1 audio/video (1080p); Socket.IO signaling; Call history (Teams-style); Screen sharing + remote pointer annotation; Group call foundation; coturn planned | 1:1 calls working (1080p); Call history complete; Screen sharing + remote pointer done; Group calls partial | Low
Phase 5 | Polish & Admin | Weeks 14–16 | 3 Weeks | Admin panel (user/group/SIP mgmt); Presence system; Performance optimization; Security hardening; User & admin documentation | Feature-complete; Security audit passed; Documentation ready | Low
Phase 6 | Testing & Deployment | Weeks 17–18 | 2 Weeks | Load test (300+ users); Security audit; Bug fixes; Production deployment; User training (300+ employees); Go-Live | 300+ concurrent users stable; All departments trained; GO-LIVE | High
Phase 5B | Email Integration (BONUS) | Week 16 | 2 Days | Stalwart internal mail server (Docker); SMTP sending; IMAP inbox per-user; Drafts, Sent, Deleted with restore; Email attachments (send + download); Contact autocomplete; Smart routing (@balasorealloys.in internal, @balasorealloys.com via O365 relay) | All email features working. 10 test accounts active. Attachments send + download working. | Low
Phase 5C | Calendar/Scheduling (BONUS) | Week 16 | 1 Day | Week/day calendar view; Create events with attendees; RSVP; Real-time invitations; Color-coded events | Events created, RSVP working, real-time notifications active | Low
Phase 5D | Internal Mail Server (BONUS) | Week 17 | 2 Days | Stalwart Mail Server in Docker Compose; @balasorealloys.in domain; Per-user IMAP/SMTP auth (mail_password); Smart SMTP routing; 10 user accounts provisioned; AD-ready for production | Stalwart running, users sending/receiving email, attachments working | Low

## Risk Register
RISK REGISTER — INTERNAL COMMUNICATION PLATFORM
# | Risk Description | Impact | Probability | Severity | Mitigation Strategy
R1 | UCM6304 hardware failure (firmware bricked device) | High | Occurred | High | MITIGATED: Pivoted to Pure WebRTC. Eliminates SIP hardware dependency entirely.
R2 | Single server = single point of failure | High | Medium | High | Regular automated backups; Monitoring + alerting; Future HA plan (post-MVP)
R3 | 300+ concurrent WebSocket connections overload | Medium | Low | Medium | Node.js handles 10K+ connections; Redis pub/sub scales horizontally if needed
R4 | File storage fills up on server | Medium | Medium | Medium | Storage monitoring dashboard; Cleanup policies; Alert at 80% threshold
R5 | Browser WebRTC compatibility issues | Low | Low | Low | All modern browsers support WebRTC; Test on Chrome, Firefox, Edge
R6 | UCM6304 firmware failure (OCCURRED) | High | Occurred | High | RESOLVED: Abandoned SIP. Adopted Pure WebRTC. Zero hardware dependency. SIP code kept as backup.
R7 | Developer resource unavailability | High | Medium | High | Cross-train team members; Document all code/architecture; Modular design
R8 | User adoption resistance (MS Teams familiarity) | Medium | Medium | Medium | Department-wise training; Quick-start guides; Feedback-driven UI improvements
R9 | SIP provisioning no longer applicable | Medium | Eliminated | None | ELIMINATED: SIP extensions not needed. Users identified by DB user ID.
R10 | Data loss during testing/migration | High | Low | Medium | Automated PostgreSQL backups; Test on separate DB instance; Rollback procedures
R11 | Network latency across subnets | Low | Low | Low | Internal network = sub-millisecond latency; coturn STUN/TURN for NAT traversal
R12 | Solo developer burnout / bus factor | High | Medium | High | Code well-structured. Architecture docs updated. Knowledge transfer possible.

## Resource Plan
RESOURCE ALLOCATION PLAN
Role | Count | Type | Phase Involvement | Key Responsibilities | Skills Required
Project Lead | 1 | Full-time | All Phases (0–6) | Overall coordination; Milestone tracking; Stakeholder communication; Risk management | Project management; Agile/Scrum; Technical architecture understanding
Full-Stack Developer (Lead) | 1 | Full-time | Phases 1–6 | Architecture decisions; Backend (Node.js/Express); Frontend (React); DB design; Code review | Node.js, React, TypeScript, PostgreSQL, Redis, Docker, WebSocket/Socket.IO
Full-Stack Developer | 1 | Full-time | Phases 1–6 | Feature development; API implementation; UI components; Testing; Bug fixes | Node.js, React, TypeScript, PostgreSQL, Socket.IO
Full-Stack Developer (Junior) | 1 | Full-time | Phases 2–6 | UI development; Chat/file components; Testing; Documentation support | React, TypeScript, HTML/CSS, REST APIs
Network/SIP Engineer | 0 | Not Needed | N/A (SIP Removed) | UCM6304 decommissioned. Pure WebRTC needs no SIP expertise. | N/A
DevOps/IT Infra | 1 | Part-time | Phases 0, 1, 5, 6 | Server provisioning; Docker deployment; CI/CD; Monitoring; Backup strategy; SSL/Nginx | Linux (Ubuntu), Docker, Nginx, SSL, Monitoring tools
QA / Tester | 1 | Part-time | Phases 5–6 | Load testing (300+ users); Security audit; Regression testing; UAT coordination | Load testing tools, Security testing, Browser testing
ACTUAL STAFFING (March 30, 2026):
Solo Developer | 1 | Full-time + Overtime | All Phases (0-6) | Single dev handling ALL roles. Delivering at 7x planned speed. 33/43 tasks + 2 BONUS modules in 20 days. | Node.js, React, TS, PostgreSQL, Redis, Docker, WebRTC, Socket.IO
NOTE: | Original plan: 2-3 developers + specialists. All work done by 1 person, 4+ months ahead of schedule.